## Pond
item number | WP | WP ID | WP Deliverable | Activities List | Cost per unit | unit per duration | Quantity | Total Cost | duration in days | Acceptance Criteria | Risks | Resources Assigned | Human Resource | Equipment | Material | Objectives | Stakeholder | Stakeholder Requirement | References | dis
building pond and linning
|  |  |  | site cleaning (subcontracting) | 0.25 | 100 | 480000 | 4800 | 20 | [9 empty] | https://books.google.com.qa/books?id=Fn3SwUueZaAC&pg=PA209&lpg=PA209&dq=shade+steel+structure+for+fish+farm&source=bl&ots=LGWRNy-A_k&sig=ACfU3U1_c1AnyjzOeJypjOvBQpq3GcuBWQ&hl=en&sa=X&ved=2ahUKEwizz5zxk4fpAhUaWX0KHR69CqYQ6AEwCnoECAoQAQ#v=onepage&q&f=false
|  |  |  | Excavating | 200 | 43.5 | 800000 | 3678160.9195 | 45.977 |  |  |  |  | 40 excavators |  |  |  |  | https://planningengineer.net/earth-moving-equipment-function-and-standard-productivity/
|  |  |  | Carry to collection | 14.56 | - | 800000 | 54945.0549 | 10
|  |  |  | Compacting &Levelling pond | 11.26 | 4200 | 60000 | 5328.5968 | 2.8571 |  |  |  |  | 5 Vibratory Roller |  |  |  |  | STANDARD PRODUCTIVITY RATES
|  |  |  | fish farming pond liner(hdpe) | 0.96 | 10000 | 480000 | 460800 | 48 | [9 empty] | STANDARD PRODUCTIVITY RATES
Construction of shade
|  |  |  | buliding steel structure | 15 |  | 480000 | 7200000 | 120 | [9 empty] | https://www.alibaba.com/product-detail/Low-Cost-Prefab-Industrial-Shed-Designs_60767642249.html?spm=a2700.galleryofferlist.0.0.3e714116XpxTy3
|  |  |  | wraping shade | 0.072 | 250 | 600000 | 43200 | 30 |  |  |  | 50 workers | [5 empty] | https://www.alibaba.com/product-detail/HDPE-Plastic-UV-Treated-Agriculture-Farming_62546812851.html?spm=a2700.galleryofferlist.0.0.3482b4efbueYBU&s=p&bypass=true

## Support System
item number | WP | WP ID | WP Deliverable | Activities List | Cost per unit | unit per duration | Quantity | Total Cost | duration in days | Acceptance Criteria | Risks | Resources Assigned | Human Resource | Equipment | Material | Objectives | Stakeholder | Stakeholder Requirement | References | dis
Solar Power system
|  |  |  | Installing Solar Panels | 5000 | 1 | 10 | 50000 | 1 | [9 empty] | https://www.alibaba.com/product-detail/Colombia-Hot-Selling-on-grid-solar_60470121347.html?spm=a2700.galleryofferlist.0.0.24a018578XVzoi
|  |  |  | Installing Solar Charge Controllers | 65 | 10 | 285.7143 | 18571.4286 | 10 | [9 empty] | https://www.alibaba.com/product-detail/Lumiax-12V-24V-40A-MPPT-Solar_60714297192.html?spm=a2700.galleryofferlist.0.0.7d792440hoHJJB
|  |  |  | Installing Battery System | 452 | 10 | 285.7143 | 129142.8571 | 10 | [9 empty] | https://www.alibaba.com/product-detail/Solar-battery-2v-2000ah-off-grid_610924741.html?spm=a2700.galleryofferlist.0.0.543b2582sfLUgb
|  |  |  | Installing Inverters | 3000 | 1 | 15 | 45000 | 1 | [9 empty] | https://www.alibaba.com/product-detail/2000W-3KW-4KW-5KW-Solar-Off_62003466366.html?spm=a2700.galleryofferlist.0.0.24a018578XVzoi
| Water treatment system |  |  |  | 8517 | 22 | 596.4286 | 242714.2857 | 22
MEP Work
Monitoring Sensors
|  |  |  | Installing pH sensors |  |  | 40 |  | 1
|  |  |  | Installing Water Level Sensors |  |  | 40 |  | 1
|  |  |  | Installing Water Temperature Sensors |  |  | 40 |  | 1
|  |  |  | Installing Oxygen concentration sensors |  |  | 40 |  | 1
Automated Harvesting System
|  |  |  | Installing Clam Shell Grader |  |  | 40 |  | 1
|  |  |  | Testing Mechanism |  |  | 40 |  | 1
Automated Feeding System
|  |  |  | Installing Feeding Tanks |  |  | 40 |  | 1
|  |  |  | Installing Feeding Mechanism |  |  | 40 |  | 1
|  |  |  | Feeding System Controller |  |  | 40 |  | 1
|  |  |  | Supplying specific feed to each pond |  |  | 40 |  | 1
Water Quality Management System
|  |  |  | Installing reverse osmosis system |  |  | 40 |  | 1
|  |  |  | Recirculating Aquaculture Filtering system |  |  | 40 |  | 1
|  |  |  | Installing Fish Waste Disposal System |  |  | 40 |  | 1
|  |  |  | Installing Mechanical Filters |  |  | 40 |  | 1
|  |  |  | Installing Bio Filters |  |  | 40 |  | 1
|  |  |  | Installing UV disinfection filters |  |  | 40 |  | 1
|  |  |  | Installing degassing filters |  |  | 40 |  | 1
|  |  |  | Installing air pumps |  |  | 40 |  | 1

## Packaging facility
item number | WP | WP ID | WP Deliverable | Activities List | Cost per unit | unit per duration | Quantity | unit | Total Cost | duration in days | Acceptance Criteria | Risks | Resources Assigned | Human Resource | Equipment | Material | Objectives | Stakeholder | Stakeholder Requirement | References | dis
SUB STRUCTURE & SUPER STRUCTURE
|  |  |  | Clearing & Grubbing | 3.8628 | 10 | 0 | Sq.M. | 0 | 0 | inspection by engineer
|  |  |  | Excavating | 7.5452 | 43 | 0 | Cu.M. | 0 | 0 | dimentional accuracy +- 75mm
|  |  |  | Filling | 11.3726 | 43 | 0 | Cu.M. | 0 | 0
|  |  |  | Disposal of material | 7.5452 | 43 | 0 | Cu.M. | 0 | 0
|  |  |  | performing Termite control treatment | 0.68219 | 20 | 0 | Sq.M. | 0 | 0 | dimentional accuracy +- 75mm
|  |  |  | Plain insitu concrete with OPC |  |  | 0 | Sq.M. |  | #DIV/0!
|  |  |  | installing Column footings |  |  | 0 | Cu.M. |  | #DIV/0!
|  |  |  | Columns & Walls up to plinth |  |  | 0 | Cu.M. |  | #DIV/0!
|  |  |  | Plinth beams |  |  | 0 | Cu.M. |  | #DIV/0!
|  |  |  | Walls |  | 0.15 | 0 | Cu.M. |  | 0 |  |  |  | 10 Mason, 10 Helper
|  |  |  | constructing Grade slab | 360 | 22 | 0 | Cu.M. | 0 | 0 | [10 empty] | https://hipages.com.au/article/cost_of_concrete_per_m3
|  |  |  | installing High yield deformed re-bar | 0.42 | 220 | 0 | Kgs. | 0 | 0 | qa/qc engineer approval & civil enginner | [9 empty] | https://www.alibaba.com/product-detail/6-8-10-12-14-16_62210784624.html?spm=a2700.7724857.normalList.2.25e2436boQDC4q&s=p&fullFirstScreen=true
|  |  |  | Finishing cont.sybstructure | 1057.5342 | 22 | 0 | Sq.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Beams / Lintels / Ribs | 178.0822 | 22 | 0 | Cu.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Columns | 167.6712 | 22 | 0 | Cu.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Slabs and Projections | 178.0822 | 22 | 0 | Cu.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Steps and staircases | 159.4521 | 22 | 0 | Cu.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Parapet Wall | 189.589 | 22 | 0 | Cu.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Walls | 189.589 | 22 | 0 | Cu.M. | 0 | 1 | qa/qc engineer approval & civil enginner
|  |  |  | Insulation | 37.2603 | 22 | 0 | Sq.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Separation Layer | 1.2411 | 22 | 0 | Sq.M. | 0 | 0 | qa/qc engineer approval & civil enginner
|  |  |  | Surfacing | 37.2603 | 22 | 0 | Sq.M. | 0 | 0 | qa/qc engineer approval & civil enginner
| Finishing (Subcontracted) |  |  | - | - |  | - | - | 194775 | 30
| Air-Conditioning Works (HVAC Works) | [7 empty] | 0 | 31
|  |  |  | Ducting & accessories | 67.1233 | 2.5 | 20 | Sq.M. | 1342.4658 | 50 | qa/qc engineer approval & MEP enginner
|  |  |  | installing Outdoor Unit (OU-UB); 10 Ton | 13698.6301 | 1 | 1 | unit | 13698.6301 | 1 | qa/qc engineer approval & MEP enginner
|  |  |  | installing indoor unit -1; 5 Ton | 5905.4795 | 1 | 2 | unit | 11810.9589 | 2 | qa/qc engineer approval & MEP enginner | [9 empty] | https://www.alibaba.com/product-detail/20TON-Rooftop-air-cooled-unit_60380990411.html?spm=a2700.details.deiletai6.8.40695fb5BztEpt&bypass=true
| Packaging System | [7 empty] | 26852.0548 | 53
|  |  |  | Installing conveyor belt system | 420 | 8 | 3 | unit | 1260 | 2.4 | qa/qc engineer approval & MEP enginner | [9 empty] | https://www.alibaba.com/product-detail/China-manufacturer-customized-conveyor-belt_60404043081.html?spm=a2700.details.deiletai6.2.4ec97704q3TO9b
|  |  |  | Installing individual Quick Freezing (QF) tunnel | 148806 | 8 | 1 | unit | 148806 | 0.8 | qa/qc engineer approval & MEP enginner | [9 empty] | https://www.alibaba.com/product-detail/Logo-Customization-Individual-Freezing-Quick-Leading_62552035480.html?spm=a2700.galleryofferlist.0.0.754e32cdbsv93Q&s=p&bypass=true
|  |  |  | Installing Bag Sealing Tape Machinery | 1980 | 8 | 1 | unit | 1980 | 0.8 | qa/qc engineer approval & MEP enginner | [9 empty] | https://www.alibaba.com/product-detail/FRM-1120LD-HUALIAN-Bag-Sealing-Tape_1507683058.html?spm=a2700.galleryofferlist.0.0.3fbe2298cdxgi1&bypass=true
| Storage system | [7 empty] | 152046 | 4
|  |  |  | Installing racks | 1.8 | 8 | 8000 | Kgs. | 14400 | 2 | qa/qc engineer approval & MEP enginner | [9 empty] | https://www.alibaba.com/product-detail/Food-Rack-System-Food-Or-Cold_62441503848.html?spm=a2700.galleryofferlist.0.0.6cbc3f9dtTBGcU&s=p&bypass=true
|  |  |  | Installing roll up doors | 3000 | 8 | 2 | unit | 6000 | 1 | qa/qc engineer approval & MEP enginner | [9 empty] | https://www.alibaba.com/product-detail/Packaging-Customization-Up-Door-Roll-Fast_60838677269.html?spm=a2700.drainage_lp_1.0.0.45e36dd0a2Z7gA&s=p&bypass=true
[9 empty] | 20400 | 3

## Admin facility
item number | WP | WP ID | WP Deliverable | Activities List | Cost per unit | unit per duration | Quantity | unit | Total Cost | duration in days | Acceptance Criteria | Risks | Resources Assigned | Human Resource | Equipment | Material | Objectives | Stakeholder | Stakeholder Requirement | References | dis
SUB STRUCTURE & SUPER STRUCTURE
|  |  |  | Clearing & Grubbing | 3.8628 | 1 | 204 | Sq.M. | 788.0037 | 204 | inspection by engineer
|  |  |  | Excavating | 7.5452 | 43 | 306 | Cu.M. | 2308.8329 | 7.1163 | dimentional accuracy +- 75mm
|  |  |  | Filling | 11.3726 | 43 | 61.2 | Cu.M. | 696.0033 | 1.4233
|  |  |  | Disposal of material | 7.5452 | 43 | 306 | Cu.M. | 2308.8329 | 7.1163
|  |  |  | performing Termite control treatment | 0.68219 | 20 | 204 | Sq.M. | 139.1671 | 10.2 | dimentional accuracy +- 75mm
|  |  |  | Plain insitu concrete with OPC |  |  | 170 | Sq.M. |  | #DIV/0!
|  |  |  | installing Column footings |  |  | 47 | Cu.M. |  | #DIV/0!
|  |  |  | Columns & Walls up to plinth |  |  | 7 | Cu.M. |  | #DIV/0!
|  |  |  | Plinth beams |  |  | 22 | Cu.M. |  | #DIV/0!
|  |  |  | Walls |  | 0.15 | 50 | Cu.M. |  | 333.3333 |  |  |  | 10 Mason, 10 Helper
|  |  |  | constructing Grade slab | 360 | 22 | 42 | Cu.M. | 15120 | 1.9091 | [10 empty] | https://hipages.com.au/article/cost_of_concrete_per_m3
|  |  |  | installing High yield deformed re-bar | 0.42 | 22 | 11700 | Kgs. | 4914 | 53.1818 | [10 empty] | https://www.alibaba.com/product-detail/6-8-10-12-14-16_62210784624.html?spm=a2700.7724857.normalList.2.25e2436boQDC4q&s=p&fullFirstScreen=true
|  |  |  | Finishing cont.sybstructure | 1057.5342 | 22 | 204 | Sq.M. | 215736.9863 | 9.2727
|  |  |  | Beams / Lintels / Ribs | 178.0822 | 22 | 65 | Cu.M. | 11575.3425 | 2.9545
|  |  |  | Columns | 167.6712 | 22 | 29 | Cu.M. | 4862.4658 | 1.3182
|  |  |  | Slabs and Projections | 178.0822 | 22 | 68 | Cu.M. | 12109.589 | 3.0909
|  |  |  | Steps and staircases | 159.4521 | 22 | 10 | Cu.M. | 1594.5205 | 1
|  |  |  | Parapet Wall | 189.589 | 22 | 7 | Cu.M. | 1327.1233 | 1
|  |  |  | Walls | 189.589 | 22 | 4 | Cu.M. | 758.3562 | 1
|  |  |  | Insulation | 37.2603 | 22 | 275 | Sq.M. | 10246.5753 | 12.5
|  |  |  | Separation Layer | 1.2411 | 22 | 275 | Sq.M. | 341.3014 | 12.5
|  |  |  | Surfacing | 37.2603 | 22 | 275 | Sq.M. | 10246.5753 | 12.5
| Finishing (Subcontracted) |  |  | - | - |  | - | - | 194775 | 30
| Air-Conditioning Works (HVAC Works) | [7 empty] | 489848.6755 | 372.0831
|  |  |  | Ducting & accessories | 67.1233 | 2.5 | 45 | Sq.M. | 3020.5479 | 112.5
|  |  |  | Outdoor Unit (OU-UB); 20 Ton | 13698.6301 | 1 | 1 | unit | 13698.6301 | 1
|  |  |  | indoor unit -1; 1 Ton | 1181.0959 | 1 | 9 | unit | 10629.863 | 9 | [10 empty] | https://www.alibaba.com/product-detail/20TON-Rooftop-air-cooled-unit_60380990411.html?spm=a2700.details.deiletai6.8.40695fb5BztEpt&bypass=true
|  |  |  | indoor unit -2; 1.3 Ton | 1181.0959 | 1 | 8 | unit | 9448.7671 | 8
[9 empty] | 36797.8082 | 130.5

## Sheet2
Work package Name /Number:Site cleaning
Work package deliverable Description: Clearing shall comprise clearing all trees, down timber, snags, bush, other vegetation, rubbish and all other objectionable material and shall include grubbing roots, stumps and matted roots etc. complete up to required depth (150mm) and / or as directed by the Engineer
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:3 days
Cost:788 usd *
Work package Name /Number: diging pond and linning
Work package deliverable Description:Excavation Carry to collection Compacting &Levelling pond fish farming pond liner(hdpe)
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:110 days
Cost:4199234 usd
Work package Name /Number: Construction of shade
Work package deliverable Description: steel structure construction and wraping of the shade
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:110 days
Cost:4199234 usd
Work package Name /Number: Construction of shade
Work package deliverable Description: steel structure construction and wraping of the shade
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:110 days
Cost:4199234 usd
Work package Name /Number: Solar Power system
Work package deliverable Description: Installing Solar Panels Installing Solar Charge Controllers Installing Battery System Installing Inverters
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:22 days
Cost: $242,714.29
Work package Name /Number: Solar Power system
Work package deliverable Description: Installing Solar Panels Installing Solar Charge Controllers Installing Battery System Installing Inverters
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:22 days
Cost: $242,714.29
Work package Name /Number: admin building substructure
Work package deliverable Description:Clearing & Grubbing,Excavating ,Filling,Disposal of material,performing Termite control treatment,constructing Grade slab,installing High yield deformed re-bar,Finishing cont.sybstructure, Beams / Lintels / Ribs,Columns,Slabs and Projections,Steps and staircases,Parapet Wall,Walls water proofing :Insulation,Separation Layer,Surfacing
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:22 days
Cost: $489,848.68
Work package Name /Number: admin building substructure & superstructure
Work package deliverable Description:Clearing & Grubbing,Excavating ,Filling,Disposal of material,performing Termite control treatment,constructing Grade slab,installing High yield deformed re-bar,Finishing cont.sybstructure, Beams / Lintels / Ribs,Columns,Slabs and Projections,Steps and staircases,Parapet Wall,Walls water proofing :Insulation,Separation Layer,Surfacing
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration:370 days
Cost: $489,848.68
Work package Name /Number: admin building MEP Work
Work package deliverable Description:Clearing & Grubbing,Excavating ,Filling,Disposal of material,performing Termite control treatment,constructing Grade slab,installing High yield deformed re-bar,Finishing cont.sybstructure, Beams / Lintels / Ribs,Columns,Slabs and Projections,Steps and staircases,Parapet Wall,Walls water proofing :Insulation,Separation Layer,Surfacing
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 131 days
Cost: $36,797.81
Work package Name /Number: admin building MEP Work
Work package deliverable Description:Ducting & accessories Outdoor Unit(evaporator) (OU-UB); 20 Ton indoor cooling unit -1; 1 Ton indoor cooling unit -2; 1.3 Ton electrical work and plumbing Work
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 131 days
Cost: $36,797.81
Work package Name /Number: packaging facility sub/super structure
Clearing & Grubbing,Excavating ,Filling,Disposal of material,performing Termite control treatment,constructing Grade slab,installing High yield deformed re-bar,Finishing cont.sybstructure, Beams / Lintels / Ribs,Columns,Slabs and Projections,Steps and staircases,Parapet Wall,Walls water proofing :Insulation,Separation Layer,Surfacing
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 374 days
Cost: $649,162.09
Work package Name /Number: packaging facility sub/super structure
Clearing & Grubbing,Excavating ,Filling,Disposal of material,performing Termite control treatment,constructing Grade slab,installing High yield deformed re-bar,Finishing cont.sybstructure, Beams / Lintels / Ribs,Columns,Slabs and Projections,Steps and staircases,Parapet Wall,Walls water proofing :Insulation,Separation Layer,Surfacing
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 374 days
Cost: $649,162.09
Work package Name /Number: packaging facility MEP WORK
Ducting & accessories installing Outdoor Unit (OU-UB); 10 Ton installing indoor unit -1; 5 Ton
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 7 days
Cost: $26,852.05
Work package Name /Number: packaging facility-Packaging System
Installing conveyor belt system Installing individual Quick Freezing (QF) tunnel Installing Bag Sealing Tape Machinery
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 4 days
Cost: $152,046.00
Work package Name /Number: packaging facility-storage System
Installing racks,Installing roll up doors
Acceptance Criteria: approved by civil engineer
Risks: worker safety, weather could cause delays
Resources assigned: Excavator
Duration: 3 days
Cost: $20,400.00

## hectare calc
consumtion | 750 | for | 40 | X | 5 | = | 200 | for | 0.5 | 400
total number of ponds | 1.875 | 9.375 tons per pond every 6 months | http://www.fao.org/3/AC155E16.htm
| HA | m^2
AREA | 40 | 400000 | https://steemit.com/engineering/@kharrazi/excavator-and-calculate-its-productivity
| m^3 | excvator m^3 per hr | number of excvator | number of hrs to excvate | days
HIGHT OF 2 m | 800000 | 120.61 | 20 | 331.6475 | 41.4559