## Pond
WP | Activities List | Cost per unit | unit per duration | Quantity | Total Cost | duration in days | Human Resource | Equipment | References | dis
building pond and linning
| site cleaning (subcontracting) | 0.25 | 100 | 480000 | 4800 | 20 |  |  | https://books.google.com.qa/books?id=Fn3SwUueZaAC&pg=PA209&lpg=PA209&dq=shade+steel+structure+for+fish+farm&source=bl&ots=LGWRNy-A_k&sig=ACfU3U1_c1AnyjzOeJypjOvBQpq3GcuBWQ&hl=en&sa=X&ved=2ahUKEwizz5zxk4fpAhUaWX0KHR69CqYQ6AEwCnoECAoQAQ#v=onepage&q&f=false
| Excavating | 200 | 43.5 | 800000 | 3678160.9195 | 45.977 |  | 40 excavators | https://planningengineer.net/earth-moving-equipment-function-and-standard-productivity/
| Carry to collection | 14.56 | - | 800000 | 54945.0549 | 10
| Compacting &Levelling pond | 11.26 | 4200 | 60000 | 5328.5968 | 2.8571 |  | 5 Vibratory Roller | STANDARD PRODUCTIVITY RATES
| fish farming pond liner(hdpe) | 0.96 | 10000 | 480000 | 460800 | 48 |  |  | STANDARD PRODUCTIVITY RATES
Construction of shade
| buliding steel structure | 15 |  | 480000 | 7200000 | 120 |  |  | https://www.alibaba.com/product-detail/Low-Cost-Prefab-Industrial-Shed-Designs_60767642249.html?spm=a2700.galleryofferlist.0.0.3e714116XpxTy3
| wraping shade | 0.072 | 250 | 600000 | 43200 | 30 | 50 workers |  | https://www.alibaba.com/product-detail/HDPE-Plastic-UV-Treated-Agriculture-Farming_62546812851.html?spm=a2700.galleryofferlist.0.0.3482b4efbueYBU&s=p&bypass=true
The Specification and Design Drawings are intended to indicate the nature and scope of the Project. The Contractor shall be responsible for the preparation of detailed coordinated working drawings and for installation of plant of the correct capacity, as per approved drawings and in line with the best prevailing engineering practices
The Contractor shall guarantee for the efficient performance of various equipment which shall not be less than the specified ratings when working under the operating conditions for respective items as shown in the drawings
All works are to be carried out in accordance with relevant internationally/ locally accepted codes of practice as well as current regulations
The Contractor to provide return air openings of suitable size at all appropriate locations
Dampers shall be placed in ducts at every branch supply, whether or not indicated on the drawings for the proper volume control and balancing of the system
The Contractor is advised to read carefully the notes on pricing for the Air-Conditioning installation while pricing works in this section
The rates for all Plumber's and Engineer’s work are to include for assembling and jointing together including jointing material; cutting and pinning in or building in all pipe and duct supports and subsequent marking good and all cutting away and making good and all pipe sleeves
The rates for ductwork to include for all joints in the running length, brackets, hangers & other supports
The rates for thermal insulation are to include for working around and over ancillaries, fittings, flanges and all other obstructions
The rates for all pipe and ductwork are to include for cutting and pinning in; building in; plugging and screwing or nailing of brackets, hangers or other supports; for all subsequent making good and for forming or cutting all holes; cutting away and making good
DUCTWORK
Galvanized sheet ductwork and fittings to SMACNA standard fixed complete to R.C. slab soffits including test holes, access panels, hanging system, supports and turning vanes/splitters for bends and and branches, bends, branch connections and transformation pieces, bell mouths, plenum boxs etc. as per drawings and specification
Ducting
| Ground floor | 45 | Sq. M.
| First floor | 30 | Sq. M.
Ducting-Joints
Approved type flexible duct connections as per drawings and specification
| Rectangular connections |  | Item
| Circular connections |  | Item
Dampers, Ducting-Turns, Access Doors and Openings as per the drawings and specification
Non Return Dampers as per drawings and specification
| Ground floor |  | Item
| First floor |  | Item
| Roof |  | Item
Volume Control Dampers of various sizes as per the drawings and specification
| Ground floor | 2 | No
Shutter, Grilles, Diffusers and Equalisers as per the drawings and specification
4 Way Air Diffusers
| Ground floor | 14 | No
| First floor | 13 | No
Return Air Grilles
| Ground floor | 6 | No
| First floor | 13 | No
Linear Slot Diffusers; 3 slots with Plenum Box as per the drawings and specification
| Ground floor |  | Item
| First floor |  | Item
| Roof |  | Item
Sub - Total (HVAC Works)
C.O. Sub - Total (HVAC Works)
Fresh and Exhaust Air Louvers; as per the drawings and specifications.
| Roof |  | Item
Fire Dampers as per drawings and specifications.
Fire Dampers with access doors
| Motorized Fire and Smoke Dampers |  | Item
| Sound Attenuators |  | Item
| Air Curtains |  | Item
THERMAL INSULATION
Insulation To Ductwork
FSK faced rigid fiberglass insulation, secured to ducts by wrapped with fiber cloth and coated with sealfas insulation as specified
| Ground floor | 45 | Sq.M.
| First floor | 30 | Sq.M.
Aluminium Cladding to Exposed Ductwork as per the drawings and specification
| Roof |  | Item
Acoustic Insulation
25 mm thick internal lined acoustic material from strong, resilient glass fibers of density not less than 48 kg/m3 bounded to ductwork with a thermosetting resin faced with black woven glass fabric as per drawings and specification
| To all duct work from the face of Indoor/ Outdoor Units/ AHU/ FAHU up to 3000 mm from the inlet/outlet of respective unit |  | Item
| 25 mm Thick internal lined acoustic insulation of 48 kg/m3 for all liner diffuser/supply air grille plenum boxes |  | Item
Sub - Total (HVAC Works)
C.O. Sub - Total (HVAC Works)
PLANT AND EQUIPMENT
Split Central DX Air Conditioning Units
Split Central DX Air Conditioning Units, working at 450C outside temperature, from an approved Manufacturer as per the drawings and specification
Refrigerant Piping with insulation and all accessories as per drawings and specifications and as recommended by the manufacturer
Variable Refrigerant Flow System VRF; Embassy Building
Variable Refrigerant Flow VRF indoor and outdoor units from an approved Manufacturer
Outdoor Units
| Outdoor Unit (OU-UB); 34 Ton | 1 | No
Indoor Units
| I.U. -1; 1 Ton | 9 | No
| I.U. -2; 1.3 Ton | 12 | No
| I.U. -3; 1.6 Ton | 2 | No
| I.U. -4; 2 Ton | 5 | No
| Refrigerant Piping with insulation and all accessories as per the drawings and specification and as recommended by the manufacturer |  | Item
Fire Rated Exhaust fans as per the drawings and specification
| EF - 1; 300 CFM Wall mounted | 8 | No
FIRE FIGHTING WORKS
Pipe works for FHR system and wet/ dry risers as per the drawings and specifications.
| 80 mm | 40 | M
| 40 mm | 5 | M
Fire Extinguishers
| Fire Extinguisher 6 kg Dry powder | 8 | No.
Accessories as per drawings & specifications
| Fire Hose reel Cabinet including | 2 | No.
Fire hose reel 30 M.
Hose valve
Fire Extinguishers (5.5 Kg, D.P. (1 No.) & Foam water 9 Lit. (1 No.)
| Fire Blanket | 1 | No.
Electrical Works
MAINS AND SUBMAINS INSTALLATION
Supply, installation, testing and commissioning of and transformers complete as detailed on the drawings and as described in the Specifications; installed on prepared base.
| Sub-main switchboard MDB-1 | 1 | No.
Distribution boards complete as detailed on the Drawings and as described in the Specification; fixing to prepared base or wall mounted.
| Distribution board DB-GF-U | 1 | No.
| Distribution board DB-FF-U | 1 | No.
Isolators complete as specified; include for supports and protection covers necessary.
| 80 Amp TPN isolator, weatherproof. | 2 | No.
CABLES
XLPE/ SWA/ PVC cables including termination as specified
| 16 mm² Four core cable | 5 | M
| 25 mm² Four core cable | 40 | M
| 120 mm² Four core cable | 100 | M
PVC / ECC cables including terminations.
| 16 mm² Single core cable | 45 | M
| 70 mm² Single core cable | 100 | M
LIGHTING INSTALLATION
Wiring to the following points in PVC cable in conduit or trunking as specified
| General lighting points | 130 | No.
| General lighting points | 44 | No.
| One-way, One-Gang switch points | 6 | No.
| One-way, Two-Gang switch points | 4 | No.
| One-way, Three-Gang switch points | 4 | No.
| Two-way switch points | 20 | No.
Sub - Total (Electrical Works)
C.O. Sub - Total (Electrical Works)
Supply and fix light fittings complete as specified and shown on drawings including all holders, ceiling roses, bulbs/fluorescent tubes and final connections; fixing in position including all necessary suspension chains, rods, brackets and support framework
GENERAL LIGHT FITTINGS
| 2x36W, T8 Surface mounted Fluorescent luminaire | 40 | No.
| 2x18W Compact Fluorescent luminaire waterproof IP45 | 16 | No.
| 50W Metal Halide luminaire (first type in the Symbols and Abbreviations table in Drawing # E-00) | 47 | No.
| 50W Metal Halide luminaire (seventh type in the Symbols and Abbreviations table in Drawing # E-00) | 12 | No.
| 50W Metal Halide luminaire (seventeenth type in the Symbols and Abbreviations table in Drawing # E-00) | 8 | No.
| Waterproof Mirror Light, IP 45 | 7 | No.
LIGHT FITTINGS WITH EMERGENCY BATTERY BACK-UP
| 2x 36W, T8 Surface mounted Fluorescent luminaire with emergency battery back-Up | 13 | No.
| 2x18W Compact Fluorescent luminaire waterproof IP45 | 4 | No.
| 50W Metal Halide luminaire (first type in the Symbols and Abbreviations table in Drawing # E-00) with emergency battery back-Up | 19 | No.
| 50W Metal Halide luminaire (seventh type in the Symbols and Abbreviations table in Drawing # E-00) with emergency battery back-Up | 7 | No.
| 50W Metal Halide luminaire (seventeenth type in the Symbols and Abbreviations table in Drawing # E-00) | 1 | No.
Supply and fix the following light switches including cover plates, grid boxes, earth terminals, phase barriers, final connections and fixing in position, all as specified.
| One-way, One-Gang switch | 6 | No.
| One-way, Two-Gang switch | 4 | No.
| One-way, Three-Gang switch | 4 | No.
| Two-way switch | 20 | No.
Sub - Total (Electrical Works)
C.O. Sub - Total (Electrical Works)
SMALL POWER INSTALLATION
Wiring to the following points in PVC cable in conduit or trunking as specified.
| 13 A Single Socket Outlet Point | 39 | No.
| 13 A Twin Socket Outlet Point | 3 | No.
| Flex Outlet Point | 11 | No.
| 20/ 45 A Double Pole Switch Point | 7 | No.
| 13A fuse Switched Spur Point for FCUs/ IDUs | 28 | No.
| Unswitched spur unit Point for CCTV cameras | 5 | No.
Supply and fix the following flush mounted general power accessories including plate boxes, earth terminals etc., final connections and fixing in position all as specified.
| 13A Single Socket Outlet | 39 | No.
| 13A Twin Socket Outlet | 3 | No.
| Flexible Outlet | 11 | No.
| 20 / 45 A Double Pole Switch | 7 | No.
| 13A fuse Switched Spur outlet for FCUs/ IDUs | 28 | No.
| Unswitched spur unit outlet for CCTV cameras | 5 | No.
CABLE TRAYS AND TRUNKING
| Galvanized steel cable trays, perforated heavy duty return flange type including supporting with sheradised threaded rods and galvanized steel heavy duty profiles. |  | Item
Galvanized steel skirting trunking complete with tees, bends, intersections etc. all as specified
| 50 x 50 mm | 1 | Item
| 100 x 100 mm | 1 | Item
DATA & TELECOMMUNICATION
TELECOMMUNICATION INSTALLATIONS
| Provide and install telephone fittings and accessories to Q-Tel approval, including all conduits and ducts with fittings, supports etc. | 1 | Item
| Telephone outlet point | 17 | No.
| Allow for block wiring as specified including TJB, Pull box etc. to complete the work in all respect and as per OOREDOO requirement. | 1 | Item

## Support System
WP | Activities List | Cost per unit | unit per duration | Quantity | Total Cost | duration in days | References
Solar Power system
| Installing Solar Panels | 5000 | 1 | 10 | 50000 | 1 | https://www.alibaba.com/product-detail/Colombia-Hot-Selling-on-grid-solar_60470121347.html?spm=a2700.galleryofferlist.0.0.24a018578XVzoi
| Installing Solar Charge Controllers | 65 | 10 | 285.7143 | 18571.4286 | 10 | https://www.alibaba.com/product-detail/Lumiax-12V-24V-40A-MPPT-Solar_60714297192.html?spm=a2700.galleryofferlist.0.0.7d792440hoHJJB
| Installing Battery System | 452 | 10 | 285.7143 | 129142.8571 | 10 | https://www.alibaba.com/product-detail/Solar-battery-2v-2000ah-off-grid_610924741.html?spm=a2700.galleryofferlist.0.0.543b2582sfLUgb
| Installing Inverters | 3000 | 1 | 15 | 45000 | 1 | https://www.alibaba.com/product-detail/2000W-3KW-4KW-5KW-Solar-Off_62003466366.html?spm=a2700.galleryofferlist.0.0.24a018578XVzoi
MEP Work
Monitoring Sensors
| Installing sensors | 6820.22 | 40 | 40 | 272808.8 | 1 | https://www.the-iot-marketplace.com/libelium-thing-lorawan-smart-fish-farming-solution-kit#/5-choose_one-eu_863_870_mhz
Automated Harvesting System
| Installing Clam Shell Grader | 1000 | 40 | 40 | 40000 | 1 | fabricated according to available
| Testing Mechanism | - | 40 | 40 | - | 1
Automated Feeding System
| Installing Feeding Mechanism | 550 | 40 | 40 | 22000 | 1
Water Quality Management System
| Installing reverse osmosis system | 1800 | 40 | 40 | 72000 | 1 | https://www.alibaba.com/product-detail/High-efficiency-water-treatment-equipment-for_60680041563.html?spm=a2700.galleryofferlist.0.0.569a6b2eY2pdDz&bypass=true
| Installing Fish Waste Disposal System | 2000 | 40 | 40 | 80000 | 1 | https://www.alibaba.com/product-detail/Fish-waste-recycling-machine-condensate-recovery_60782955935.html?spm=a2700.galleryofferlist.0.0.6adb595cWD9vYN
| Installing Mechanical Filters | 3400 | 40 | 40 | 136000 | 1 | https://www.alibaba.com/product-detail/Aquaculture-fish-farm-drum-filter-for_60704241767.html?spm=a2700.galleryofferlist.0.0.af2f192bvvYtmw&s=p
| Installing Bio Filters | 1000 | 40 | 40 | 40000 | 1 | https://www.alibaba.com/product-detail/Fish-pond-recirculation-water-aquaculture-bio_60607468311.html?spm=a2700.galleryofferlist.0.0.37417988r57p8P
| Installing UV disinfection filters | 2500 | 40 | 40 | 100000 | 1 | https://www.alibaba.com/product-detail/Aquacultural-Fish-Farm-Circulating-Water-Disinfection_60510886638.html?spm=a2700.galleryofferlist.0.0.5563626dAVBEag&s=p
| Installing degassing filters | 6932 | 40 | 40 | 277280 | 1 | https://www.alibaba.com/product-detail/Chinese-factory-co2-degassing-for-ras_62540604689.html?spm=a2700.galleryofferlist.0.0.3cc24c21exnYPN&bypass=true
| Installing air pumps | 450 | 40 | 40 | 18000 | 1 | https://www.alibaba.com/product-detail/220V-700w-air-pump-for-fish_1863126221.html?spm=a2700.galleryofferlist.0.0.418e529aD7x0Gq&s=p

## Packaging facility
WP | Activities List | Cost per unit | unit per duration | Quantity | unit | Total Cost | duration in days | Acceptance Criteria | References
SUB STRUCTURE & SUPER STRUCTURE
| Clearing & Grubbing | 3.8628 | 10 | 448.8 | Sq.M. | 1733.6082 | 44.88 | inspection by engineer
| Excavating | 7.5452 | 43 | 673.2 | Cu.M. | 5079.4323 | 15.6558 | dimentional accuracy +- 75mm
| Filling | 11.3726 | 43 | 134.64 | Cu.M. | 1531.2072 | 3.1312
| Disposal of material | 7.5452 | 43 | 673.2 | Cu.M. | 5079.4323 | 15.6558
| performing Termite control treatment | 0.68219 | 20 | 448.8 | Sq.M. | 306.1677 | 22.44 | dimentional accuracy +- 75mm
| Plain insitu concrete with OPC |  |  | 374 | Sq.M. |  | #DIV/0!
| installing Column footings |  |  | 103.4 | Cu.M. |  | #DIV/0!
| Columns & Walls up to plinth |  |  | 15.4 | Cu.M. |  | #DIV/0!
| Plinth beams |  |  | 48.4 | Cu.M. |  | #DIV/0!
| Walls |  | 0.15 | 110 | Cu.M. |  | 733.3333
| constructing Grade slab | 360 | 22 | 92.4 | Cu.M. | 33264 | 4.2 |  | https://hipages.com.au/article/cost_of_concrete_per_m3
| installing High yield deformed re-bar | 0.42 | 220 | 25740 | Kgs. | 10810.8 | 117 | qa/qc engineer approval & civil enginner | https://www.alibaba.com/product-detail/6-8-10-12-14-16_62210784624.html?spm=a2700.7724857.normalList.2.25e2436boQDC4q&s=p&fullFirstScreen=true
| Finishing cont.sybstructure | 1057.5342 | 22 | 448.8 | Sq.M. | 474621.3699 | 20.4 | qa/qc engineer approval & civil enginner
| Beams / Lintels / Ribs | 178.0822 | 22 | 143 | Cu.M. | 25465.7534 | 6.5 | qa/qc engineer approval & civil enginner
| Columns | 167.6712 | 22 | 63.8 | Cu.M. | 10697.4247 | 2.9 | qa/qc engineer approval & civil enginner
| Slabs and Projections | 178.0822 | 22 | 149.6 | Cu.M. | 26641.0959 | 6.8 | qa/qc engineer approval & civil enginner
| Steps and staircases | 159.4521 | 22 | 22 | Cu.M. | 3507.9452 | 1 | qa/qc engineer approval & civil enginner
| Parapet Wall | 189.589 | 22 | 15.4 | Cu.M. | 2919.6712 | 0.7 | qa/qc engineer approval & civil enginner
| Walls | 189.589 | 22 | 8.8 | Cu.M. | 1668.3836 | 1 | qa/qc engineer approval & civil enginner
| Insulation | 37.2603 | 22 | 605 | Sq.M. | 22542.4658 | 27.5 | qa/qc engineer approval & civil enginner
| Separation Layer | 1.2411 | 22 | 605 | Sq.M. | 750.863 | 27.5 | qa/qc engineer approval & civil enginner
| Surfacing | 37.2603 | 22 | 605 | Sq.M. | 22542.4658 | 27.5 | qa/qc engineer approval & civil enginner
Finishing (Subcontracted) | - | - |  | - | - | 194775 | 30
Air-Conditioning Works (HVAC Works) | [5 empty] | 649162.0861 | 374.7628
| Ducting & accessories | 67.1233 | 2.5 | 20 | Sq.M. | 1342.4658 | 50 | qa/qc engineer approval & MEP enginner
| installing Outdoor Unit (OU-UB); 10 Ton | 13698.6301 | 1 | 1 | unit | 13698.6301 | 1 | qa/qc engineer approval & MEP enginner
| installing indoor unit -1; 5 Ton | 5905.4795 | 1 | 2 | unit | 11810.9589 | 2 | qa/qc engineer approval & MEP enginner | https://www.alibaba.com/product-detail/20TON-Rooftop-air-cooled-unit_60380990411.html?spm=a2700.details.deiletai6.8.40695fb5BztEpt&bypass=true
Packaging System | [5 empty] | 26852.0548 | 53
| Installing conveyor belt system | 420 | 8 | 3 | unit | 1260 | 2.4 | qa/qc engineer approval & MEP enginner | https://www.alibaba.com/product-detail/China-manufacturer-customized-conveyor-belt_60404043081.html?spm=a2700.details.deiletai6.2.4ec97704q3TO9b
| Installing individual Quick Freezing (QF) tunnel | 148806 | 8 | 1 | unit | 148806 | 0.8 | qa/qc engineer approval & MEP enginner | https://www.alibaba.com/product-detail/Logo-Customization-Individual-Freezing-Quick-Leading_62552035480.html?spm=a2700.galleryofferlist.0.0.754e32cdbsv93Q&s=p&bypass=true
| Installing Bag Sealing Tape Machinery | 1980 | 8 | 1 | unit | 1980 | 0.8 | qa/qc engineer approval & MEP enginner | https://www.alibaba.com/product-detail/FRM-1120LD-HUALIAN-Bag-Sealing-Tape_1507683058.html?spm=a2700.galleryofferlist.0.0.3fbe2298cdxgi1&bypass=true
Storage system | [5 empty] | 152046 | 4
| Installing racks | 1.8 | 8 | 8000 | Kgs. | 14400 | 2 | qa/qc engineer approval & MEP enginner | https://www.alibaba.com/product-detail/Food-Rack-System-Food-Or-Cold_62441503848.html?spm=a2700.galleryofferlist.0.0.6cbc3f9dtTBGcU&s=p&bypass=true
| Installing roll up doors | 3000 | 8 | 2 | unit | 6000 | 1 | qa/qc engineer approval & MEP enginner | https://www.alibaba.com/product-detail/Packaging-Customization-Up-Door-Roll-Fast_60838677269.html?spm=a2700.drainage_lp_1.0.0.45e36dd0a2Z7gA&s=p&bypass=true
[6 empty] | 20400 | 3
204
306
61.2
306
204
170
47
7
22
50
42
11700
204
65
29
68
10
7
4
275
275
275

## Admin facility
item number | WP | WP ID | Activities List | Cost per unit | unit per duration | Quantity | unit | Total Cost | duration in days | References
SUB STRUCTURE & SUPER STRUCTURE
|  |  | Clearing & Grubbing | 3.8628 | 1 | 204 | Sq.M. | 788.0037 | 10.2
|  |  | Excavating | 7.5452 | 43 | 306 | Cu.M. | 2308.8329 | 7.1163
|  |  | Filling | 11.3726 | 43 | 61.2 | Cu.M. | 696.0033 | 1.4233
|  |  | Disposal of material | 7.5452 | 43 | 306 | Cu.M. | 2308.8329 | 7.1163
|  |  | performing Termite control treatment | 0.68219 | 20 | 204 | Sq.M. | 139.1671 | 10.2
|  |  | Plain insitu concrete with OPC |  |  | 170 | Sq.M. |  | #DIV/0!
|  |  | installing Column footings |  |  | 47 | Cu.M. |  | #DIV/0!
|  |  | Columns & Walls up to plinth |  |  | 7 | Cu.M. |  | #DIV/0!
|  |  | Plinth beams |  |  | 22 | Cu.M. |  | #DIV/0!
|  |  | Walls |  | 0.15 | 50 | Cu.M. |  | 333.3333
|  |  | constructing Grade slab | 360 | 22 | 42 | Cu.M. | 15120 | 1.9091 | https://hipages.com.au/article/cost_of_concrete_per_m3
|  |  | installing High yield deformed re-bar | 0.42 | 22 | 11700 | Kgs. | 4914 | 53.1818 | https://www.alibaba.com/product-detail/6-8-10-12-14-16_62210784624.html?spm=a2700.7724857.normalList.2.25e2436boQDC4q&s=p&fullFirstScreen=true
|  |  | Finishing cont.sybstructure | 1057.5342 | 22 | 204 | Sq.M. | 215736.9863 | 9.2727
|  |  | Beams / Lintels / Ribs | 178.0822 | 22 | 65 | Cu.M. | 11575.3425 | 2.9545
|  |  | Columns | 167.6712 | 22 | 29 | Cu.M. | 4862.4658 | 1.3182
|  |  | Slabs and Projections | 178.0822 | 22 | 68 | Cu.M. | 12109.589 | 3.0909
|  |  | Steps and staircases | 159.4521 | 22 | 10 | Cu.M. | 1594.5205 | 1
|  |  | Parapet Wall | 189.589 | 22 | 7 | Cu.M. | 1327.1233 | 1
|  |  | Walls | 189.589 | 22 | 4 | Cu.M. | 758.3562 | 1
|  |  | Insulation | 37.2603 | 22 | 275 | Sq.M. | 10246.5753 | 12.5
|  |  | Separation Layer | 1.2411 | 22 | 275 | Sq.M. | 341.3014 | 12.5
|  |  | Surfacing | 37.2603 | 22 | 275 | Sq.M. | 10246.5753 | 12.5
|  |  | Finishing (Subcontracted) | - |  | - | - | 253207.5 | 30
| Air-Conditioning Works (HVAC Works) | [6 empty] | 548281.1755 | 178.2831
|  |  | Ducting & accessories | 67.1233 | 2.5 | 45 | Sq.M. | 3020.5479 | 112.5
|  |  | Outdoor Unit (OU-UB); 20 Ton | 13698.6301 | 1 | 1 | unit | 13698.6301 | 1
|  |  | indoor unit -1; 1 Ton | 1181.0959 | 1 | 9 | unit | 10629.863 | 9 | https://www.alibaba.com/product-detail/20TON-Rooftop-air-cooled-unit_60380990411.html?spm=a2700.details.deiletai6.8.40695fb5BztEpt&bypass=true
|  |  | indoor unit -2; 1.3 Ton | 1181.0959 | 1 | 8 | unit | 9448.7671 | 8
[8 empty] | 36797.8082 | 130.5

## hectare calc
consumtion | 750 | for | 40 | X | 5 | = | 200 | for | 0.5 | 400
total number of ponds | 1.875 | 9.375 tons per pond every 6 months | http://www.fao.org/3/AC155E16.htm
| HA | m^2
AREA | 40 | 400000 | https://steemit.com/engineering/@kharrazi/excavator-and-calculate-its-productivity
| m^3 | excvator m^3 per hr | number of excvator | number of hrs to excvate | days
HIGHT OF 2 m | 800000 | 120.61 | 20 | 331.6475 | 41.4559